**Programming Data Science**

**Timeline**

**Team members:**

* Mostapha Ahaduch 7364245
* Emre Yildiz 7364253
* Marco Kurka 7369099
* Tim Rittich 7371596
* Erkin Altuntas 7323082

Team meetings take place every Monday at 6 PM via zoom. There is planned at least one meeting per week.

**Task 1 Exploration and Description** *(1 - 2 weeks)*

The team decided that each member should do the first task on your own to get a basic understanding for the corresponding data.

The first results on data exploration and description will be collected at the first real team meeting on April 20th . The latest deadline for this task is scheduled to April 27th.

**Task 2 Visualization** *(max. 2 weeks)*

Work on data visualization tasks starts on April 28th at the latest. The first results will be discussed at the team meeting on May 4th. The tasks for the visualization part should be completed until the next team meeting on May 11th.

**Task 3 Prediction** *(max. 3 weeks)*

The longest working duration are planned for predictions tasks. The process on the predictive tasks will be communicate at the team meetings every week. The team wants to conclude the project until the end of May. The first week of July can be used as a time buffer to fix some things on the results until the Hackathon takes place on July 8th.

The final presentation will be on July 11th.